## Slide 1: Watson for IBM Cloud Private Engagement Overview <CUSTOMER> <DATE>

## Slide 2
What is the Watson for IBM Cloud Private Offering?
WATSON FOR IBM CLOUD PRIVATE
2 Weeks
Discovery
Discovery
Adoption & Integration
Operational Readiness
Assess readiness to deploy IBM Cloud Private and Watson
Client gets:
A high level assessment of client’s readiness with respect to people, processes and environment prior to deployment of IBM Cloud Private
Deploy IBM Cloud Private and Watson
Client gets:
IBM Cloud Private platform integrated with Watson and ready for development of first use case.
Prepares you for operation of your Watson environment
Client gets:
Knowledge transfer to perform core ongoing operational responsibilities such as, health monitoring, housekeeping, upgrades and troubleshooting

## Slide 3: Activity 1 - Conduct Remote Assessment
Purpose
Prepare for the IBM Cloud Private (ICP) deployment
IBM Tasks
Conduct a working session with <CUSTOMER> to review ICP implementation guidelines and requirements
Provide guidance on capacity and sizing information requirements needed for ICP including compute, network and storage resources
Present prerequisites needed for ICP and other technologies that will be initiated as part of the solution
IBM will engage <CUSTOMER>
Ensure your platform architects and operations team subject matter experts are present at the meeting, to identify target systems for the ICP installation, work through the prerequisites document and ensure the prerequisites are satisfied
Deliverables
ICP prerequisite documentation
Completion Criteria
IBM has conducted the working session and provided the ICP prerequisite documentation.

## Slide 4: Activity 2 - Watson ICP Discovery Workshop
Purpose
Verify readiness to implement the IBM Cloud Private topology
IBM Tasks
Conduct an on-site workshop, where IBM will validate the business and technical requirements for the <CUSTOMER> Solution
Review and evaluate completion status of deliverables from Activity 1 and identify next steps required to proceed to the next activity
IBM will engage <CUSTOMER>
Ensure your platform architects and operations team subject matter experts are present at the meeting. Provide IBM specific project objectives including details and implementation requirements necessary for completion of the items to be delivered on this SOW. Provide IBM with the logistics to access the installation systems
Separately obtain the appropriate Watson and IBM Cloud Private entitlements
Deliverables
Solution Workshop Findings Readout
Completion Criteria
Completion of the workshop and delivery of the Solution Workshop Findings Readout.

## Slide 5: Activity 3 - IBM Cloud Private Initiation
Purpose
Perform ICP deployment activities to support the target non-production Solution topology.
IBM Tasks
Install a single instance of IBM Cloud Private components including: 1 Boot node, 1 Master node, 1 Management node, 1 Proxy node and up to 10 Worker Nodes.
Integrate IBM Cloud Private with a supported LDAP Directory;
Provide knowledge and information transfer on Cloud Service Management and Operations concepts throughout the deployment;
Deploy the services stack (as entitled by the Client) and other components required to manage the platform;
Deploy one IBM provided sample application to be used as a reference example;
Perform functional testing to validate agreed upon success criteria defined in Activity 2; and
Document the deployed solution in a configuration document
IBM will engage <CUSTOMER>
Provide the necessary prerequisites for IBM Cloud Private as defined in Activity 1 and validated in Activity 2.
Participate in the technical knowledge transfer session with IBM to be enabled on the installation process
Provide necessary resources if needed to support or troubleshoot any hardware or connectivity issues.
Deliverables
Configuration Document
Completion Criteria
IBM has installed IBM Cloud Private and provided a demonstration of the example application.

## Slide 6: Activity 4 - IBM Cloud Private Configuration for Watson
Purpose
Install and configure a non-production Instance of the selected Watson Service on the IBM Cloud Private platform.
IBM Tasks
Install the Watson Service to IBM Cloud Private
Provide knowledge and information transfer throughout the deployment
Perform functional testing to validate Watson Service operation
IBM will engage <CUSTOMER>
Participate in the technical knowledge transfer session with IBM to be enabled on the installation process.
Deliverables
Configuration Document
Completion Criteria
IBM has installed the IBM Watson Assistant Service and the IBM Watson Speech to Text service on IBM Cloud Private

## Slide 7: Activity 5 - Operational Workshop
Purpose
Prepare <CUSTOMER> to maintain the Watson on ICP Services operation.
IBM Tasks
Conduct a one day session with <CUSTOMER> on a mutually agreed upon date after installation has completed.
IBM will engage <CUSTOMER>
Participate in the technical knowledge transfer session with IBM to be enabled on the installation process.
Deliverables
None
Completion Criteria
IBM has conducted the workshop

## Slide 8: Deliverables
Item to be delivered | Purpose and Content | Deliverable Type | Delivery method (soft copy unless otherwise specified)
IBM Cloud Private (ICP) Prerequisite Documentation * | Bookmarks / reference URL(s) | Project Material | One (1) soft copy document
Solution Workshop Findings Readout * | Slide deck outlining the discussion and architectural decisions | Project Material | One (1) soft copy document
Configuration Document * | Word document outlining the configuration deployed for the Solution | Project Material | One (1) soft copy document
* Includes IBM Existing Works. |  |  | 

## Slide 9: Estimated Schedule

## Slide 10: Key Contacts and escalation points
Role |  |  |  | 

## Slide 11: Wrap Up
Action Items
Next Steps
Questions

## Slide 12
Proposed deployment topology – Non-Prod
Master
Worker Node
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
Proxy Node
Boot Node
Worker Node
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
Worker Node
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
Storage Device(s)
Storage Device(s)
Storage Device(s)
Persistent
Storage
Cluster
Heketi
GlusterFS Node
GlusterFS Node
GlusterFS Node
Management Node
One Non-Production ICP Topology will be installed
Master Node (with Boot Node)
? Worker Nodes <Update for engagement>
1 Proxy Node
1 Management Node
Note: Additional worker nodes can be added as workload dictates
**IF USED** Three node Gluster Cluster including Heketi (cohosted with one of the GlusterFS nodes
3 GlusterFS Nodes
1 Heketi Node
Note: Additional storage nodes can be added at any time.
WATSON FOR IBM CLOUD PRIVATE
Cloud Foundry
Use Deployment topology appropriate for engagement
Notes: This is an example that should be used for a standard 5 node install with GlusterFS. Remove if not using Gluster. Alter number of nodes as you see fit.

## Slide 13
Proposed deployment topology - HA
One HA ICP Topology will be installed
3 Master Nodes (with Boot Node)
? Worker Nodes <Update for engagement>
3 Proxy Nodes
3 Management Nodes
Note: Additional worker nodes can be added as workload dictates. At 50 worker nodes best-practices adding additional master nodes always keeping the number odd.
**IF USED** Three node Gluster Cluster including Heketi (cohosted with one of the GlusterFS nodes
3 GlusterFS Nodes
1 Heketi Node
Note: Additional storage nodes can be added at any time.
Master Node
Worker Node 1
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
Proxy Node
Worker Node 2
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
Worker Node N
Pod
Container
Container
Pod
Container
Container
Pod
Container
Container
Docker
VIP
VIP
VIP
VIP
Storage Device(s)
Storage Device(s)
Storage Device(s)
Persistent
Storage
Cluster
Heketi
GlusterFS Node
GlusterFS Node
GlusterFS Node
Master Node
Master Node
Boot Node
Proxy Node
Proxy Node
VIP
VIP
Cloud Foundry
Management Node
Management Node
Management Node
WATSON FOR IBM CLOUD PRIVATE
Use Deployment topology appropriate for engagement

## Slide 14
IBM Cloud Private
Example
WATSON FOR IBM CLOUD PRIVATE